Water Operator Annual Report

2022

Water quality is very good and tested monthly for Total Coliform and e-coli at Red River lab.  Tests are also done yearly for chlorination by-products.  Lead and Copper tests are done every three years.  The NM Environment Department does a thorough chemical analysis of nitrates and nitrites yearly and additional chemical tests every five years. Results are updated yearly and posted on SCMDWCA.org website. A yearly CCR (Community Confidence Report) is posted yearly (July) with updated data on water analysis and any system violations.

Improvements on System this past year-

- New clean out valve between the infiltration gallery and water tank.  Flush quarterly to remove accumulated silt. (completed by Redwolf Plumbing)

- Pressure relief valve put in at Trini Cordova’s meter box due to high pressure at end of domestic line.

- Hydrants (3) flushed monthly instead of quarterly.

- New water hookup for Mr. Carey Smith

Future needs-

- Water tank needs to be refinished inside due to interior rust spots.

- New pressure relief valves at vaults at north entrance to valley and on VonDorp’s property.  The north entrance vault needs to be replaced due to difficulty accessing the PRValve inside it.

- New radio read meters for leak monitoring and year-long reading of meters (not just April – October). Most canisters will need to be replaced for new meters due to old (1973) inlet pipes and lack of turn-off valves. (Phase two of construction plans)

- Due to increase costs for meter installation (now close to $1800), is the current membership fee of $2,000 sufficient?

Construction of Treatment Plant

- Construction completion date is March 26, 2022 but with weekly snow since the first of the year – crews can’t access the site.  Last week, over 18 inches of packed snow at site.

- To be completed by contractor:

-Vault plumbing: main meter, altitude valve, filter all need to be installed (2 days)

-Installation of main water lines from vault to tank and distribution line (2 days)

-Electrical work to be completed in vault (1 day)

-Remove old vault and regrade the site (1 day)

-To be completed by SC domestic water:

-Complete installation of by-pass line and external frost-free hydrant (1 day)

-Insulate and drywall new vault walls and ceiling as well as old storage shed.

(2 days)

Any questions, feel free to contact Jim Gilroy at 776-8450 or email: gilroy@unm.edu

Jim is a “small water” certified operator - license no. NM 12299,